## Sheet1
Task | Sub Task | Weeks
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Create logo | Draw shapes and text | bar: Weeks Week 1
Design the system | Choose typography and structure of layout | bar: Weeks Week 1 to Weeks Week 2
Enter data into system | Create fake names and information | bar: Weeks Week 2
Enter formula into system | Create VLOOKUPs, COUNTIFs and others | bar: Weeks Week 3 to Weeks Week 4
Set up mail merge fields | Create individual fields for Name, Address and others | bar: Weeks Week 5
Create booking invoice | Use the mail-merge wizard to link invoice to system | bar: Weeks Week 5 to Weeks Week 6
Set up data validation | Add in dropdowns, error messages and cell protection | bar: Weeks Week 7 to Weeks Week 8
Create Quick-Peek form | Create different sections of form, program VBA functions | bar: Weeks Week 9
Refine design of system | Check usage of colours, typography, and user experience | bar: Weeks Week 10
Modify the system | Change usage of certain formulas, etc… | bar: Weeks Week 11
Evaluate system | Complete evidence of solution | bar: Weeks Week 12